IMPLANR

Dental College App + Dental Clinic App

Project Timeline & Payment Milestones

Project Overview

| Phase | Work | Duration | Payment |
| --- | --- | --- | --- |
| Phase 1 | App Separation + Backend Foundation | 3 weeks | ₹25,000 |
| Phase 2 | Signup + Subscription + Testing | 3 weeks | ₹20,000 |
| Phase 3 | Store Listing + Publishing | 2 weeks | ₹15,000 |
| Total |  | ~8 weeks | ₹60,000 |

Phase 1 — App Separation + Backend Foundation

| Phase Phase 1 | Duration 3 weeks | Payment ₹25,000 |
| --- | --- | --- |

Payment due at project kickoff / start.

Why ₹25,000 Upfront?

This is not a blank-slate project. The existing app is a production-grade system — 13,000+ lines of backend code, 100+ frontend screens, 15 implant brand protocols, AI integrations, HIPAA compliance features, and 103 automated tests. Splitting this into two separate apps is a high-precision task: every screen, route, navigation flow, and backend endpoint must be untangled correctly without breaking any existing functionality.

Phase 1 is the foundation everything else depends on. If this is done wrong, Phase 2 and Phase 3 break. The advance covers 3 weeks of dedicated senior-level work on a complex, already-live codebase — not a simple copy-paste job.

App Separation

- Fork existing codebase into 2 separate Expo projects:

- implanr-college — for dental colleges (students, supervisors, nurses)

- implanr-clinic — for dental clinics (dentists, assistants)

- Remove college-specific screens from clinic app

- Remove clinic-specific screens from college app

- Clean navigation and tab structure per app

- Backend: add organizations collection, org_type field on users, subscription_status field

- Configure 2 separate EAS projects with unique bundle IDs:

- College: com.implanr.college

- Clinic: com.implanr.clinic

AWS Deployment Setup

- Launch EC2 instance (Ubuntu, t3.medium recommended for production)

- Install Python, Gunicorn + Uvicorn, configure gunicorn.conf.py

- Deploy FastAPI backend, set up as systemd service (auto-restart on crash)

- Configure S3 bucket for file storage (consent forms, CBCT scans, case photos)

- Set up IAM user with least-privilege policy for S3 access

- Point domain/subdomain to EC2 (e.g. api.implanr.com)

- SSL certificate via Let’s Encrypt (HTTPS enforced, HTTP blocked)

- MongoDB Atlas connected to EC2 (whitelist EC2 IP)

- Environment variables secured via .env on server (not committed to code)

- Nginx as reverse proxy in front of Gunicorn

- Basic CloudWatch or UptimeRobot monitoring for uptime alerts

Phase 1 Deliverable

Both apps running correctly on simulator — each showing only screens relevant to its audience. Backend live on AWS with HTTPS, accessible from both apps.

Phase 2 — Signup Flow + Subscription + Testing

| Phase Phase 2 | Duration 3 weeks | Payment ₹20,000 |
| --- | --- | --- |

Payment due at Phase 2 kickoff (after Phase 1 complete).

Milestone 2A — Signup Flow + Razorpay (Week 1–2)

Signup Flow (both apps)

- Multi-step registration:

- Step 1: Organization setup (college name / clinic name, location)

- Step 2: Admin account creation (name, email, password)

- Step 3: Invite link/code generated for team members

- Step 4: Team joins via invite → picks role (student/supervisor or dentist/assistant)

- Backend endpoints:

- POST /organizations — create org

- POST /organizations/invite — generate invite token

- GET /organizations/join/:token — validate + pre-fill signup

Razorpay Subscription (web portal)

- Simple web portal with subscription plans:

- College: Starter (₹199/mo), Standard (₹349/mo), Enterprise (custom)

- Clinic: Solo (₹29/mo), Small (₹79/mo), Large (₹149/mo)

- Razorpay checkout → webhook → backend activates subscription

- Backend endpoints: POST /webhooks/razorpay, GET /organizations/:id/status

- Both apps check subscription on login → if inactive → redirect to website

- No Razorpay inside app (Apple/Google policy — payment handled on web only)

Milestone 2A Deliverable

Complete signup flow live on both apps + subscription activation working end-to-end (test mode).

Milestone 2B — Testing + QA (Week 2–3)

- Manual QA: all flows, both apps, both platforms (iOS + Android)

- Device testing:

- iOS: iPhone SE, iPhone 12, iPhone 15

- Android: Samsung mid-range, Pixel 7

- iPad: tablet layout check

- Backend load test (50+ concurrent users)

- Razorpay test mode → production mode switch

- Fix all bugs found during QA

- TestFlight builds (college + clinic) sent to client for review

- Play Store Internal Testing builds sent to client

Milestone 2B Deliverable

Client-approved builds on TestFlight and Play Store Internal Testing. Razorpay live and processing real payments.

Phase 3 — Store Listing + Publishing

| Phase Phase 3 | Duration 2 weeks | Payment ₹15,000 |
| --- | --- | --- |

Payment due when both apps are live on both stores.

App Store (iOS) — Both Apps

- App Store Connect listings created for college app + clinic app

- Screenshots for iPhone 6.7", 6.5", 5.5" and iPad 12.9"

- App description, keywords, category (Medical)

- Privacy manifest (PrivacyInfo.xcprivacy) — required iOS 17+

- Privacy policy URL live on web

- Age rating: 4+

- Submit for review

Play Store (Android) — Both Apps

- Google Play Console listings created for college app + clinic app

- Feature graphic (1024×500) + screenshots for phone + tablet

- App description, category (Medical)

- Data safety form filled (PHI handling declared)

- Content rating questionnaire completed

- Submit for review

Review Handling

- Monitor both stores daily during review (typical: 1–3 business days)

- Respond to any App Review queries within 24 hours

- Fix and resubmit if rejected

*Note : Timeline excludes delays caused by App Store / Play Store review processes.

Phase 3 Deliverable

Both apps live and publicly available on App Store + Play Store.

Payment Schedule

| When | Amount | For |
| --- | --- | --- |
| Project kickoff | ₹25,000 | Phase 1 start |
| Phase 1 complete | ₹20,000 | Phase 2 start |
| Phase 2 complete (TestFlight approved) | ₹15,000 | Phase 3 start |
| Both apps live on stores | — | Phase 3 already paid at start |
| Total | ₹60,000 |  |

One-Time Setup Costs (Client Pays Directly)

| Item | Cost |
| --- | --- |
| AWS account + EC2 instance setup | ~₹500–1,500/month (client’s AWS account) |
| S3 bucket (file storage) | ~₹50–200/month depending on usage |
| MongoDB Atlas (M10 production cluster) | ~₹5,000/month |
| Razorpay account | Free (client registers) |

Notes

- Client responsible for providing app icons and final app name before Phase 3

- Privacy policy and Terms of Use must be live on a public URL before store submission (client’s responsibility to get legal review)